## Agile Project Planning
Assignment 1: Agile Project Planning - Create a one-page project plan for a new software feature using Agile planning techniques. Include backlog items with estimated story points and a prioritized list of user stories?
Create a online flight booking project plan for a new software feature using Agile planning techniques
User Story Id |  | Userstory Name | Userstory step definition | [5 empty] | Assinged To | Estimated Time | Actual Time | Status
User 1 |  | User Login | As a<type of user> | I want to <Perform some task> |  | So that I can <Achieve some goal> | Priority | Story Points | Ragul | 2 days | 1 day | Complete
|  |  | As a user | I want to log in using my email and password |  | So that I can access my account | High | 5 | Sachin | 1 day | 1 day | Complete
|  |  | As a user | I want to be able to reset my password |  | so I can regain access to my account. | High | 5 | Seshu | 3 days | 2 days | InProgress
|  |  | As a user | I want to log in using my social media accounts |  | so, the user can login for their convience | High | 5 | Venkatesh | 4 days | 3 days | Complete
|  |  | As a user | I want to see an error message |  | if I enter invalid details, so I know to try again | Low | 3 | Priyanka | 8 hrs | 1 days | InProgress
|  |  | As a user | I want to receive a notification email |  | Whether, there's login a new device | High | 8 | Shallini | 1 day | 2 days | Complete
User 2 |  | Ticket Booking | As a user | I want to search flight by entering depart and dest. |  | So that I can able to select flight | Low | 3 | Sainadh | 1 day | 1 day | Complete
|  |  | As a user | I want to filter by price,dep time, availablity,.. |  | so that user can able to select per preference | Low | 3 | Mayank | 3 days | 3 days | Complete
|  |  | As a user | I want to sort search results by price, duration,time |  | so, the user can able to select per preference | Medium | 5 | Venkatesh | 4 days | 5 days | InProgress
|  |  | As a user | I want to review my details before confirming |  | so I can ensure everything is correct. | High | 8 | sathish | 8 hrs | 1 day | InProgress
|  |  | As a user | make payments securely using my preferred method |  | so I can complete my booking | High | 8 | sai | 1 day | 1 day | Complete
|  |  | As a user | I want to receive a confirmation email |  | so I have proof of purchase and travel information. | High | 8 | mayank | 1 day | 1 day | Complete
User 3 |  | Payment | As a user | I want to enter my payment details securely |  | to complete my booking. | High | 8 | Sachin | 1 day | 1 day | Complete
|  |  | As a user | want see a summary of flight details and total cost |  | so I can verify the information. | High | 8 | Seshu | 3 days | 2 days | Complete
|  |  | As a user | want the payment page to support multiple currency |  | so I can pay in my preferred currency. | High | 8 | Sainadh | 4 days | 4 days | Complete
|  |  | As a user | I want to apply discount codes or promotions |  | to reduce my total cost. | Low | 3 | Priyanka | 8 hrs | 6 hrs | Complete
|  |  | As a user | I want to save my payment detail securely for future |  | so I don't have to enter them again. | High | 5 | Mayank | 1 day | 1 day | Complete
|  |  | As a user | I want to receive an immediate confirmation email |  | so I know my booking is confirmed. | High | 5 | Shallini | 1 day | 1 day | InProgress
User 4 |  | Feedback | As a user | I want to provide a rating for booking experience |  | so I can share my satisfaction level. | High | 5 | Sachin | 1 day | 1 day | InProgress
|  |  | As a user | I want to write a review of my booking experience |  | so I can give detailed feedback | Low | 3 | Seshu | 3 days | 4 days | InProgress
|  |  | As a user | I want to view other users' ratings and reviews |  | so I can make informed decisions about booking. | Low | 3 | Venkatesh | 4 days | 3 days | Complete
|  |  | As a admin | I want to monitor and moderate user reviews |  | I can ensure arch is appropriate and constructive. | Low | 3 | Sai | 8 hrs | 8 hrs | Complete
|  |  | As a user | I want to filter reviews by rating, date, and relevance |  | so I can quickly find the most useful feedback. | Low | 3 | Shallini | 1 day | 1 day | Complete
|  |  | As a admin | I want to generate reports on user feedback |  | so I can identify trends and areas for improvement. | High | 8 | Shallini | 1 day | 1 day | InProgress
User 005 |  | Admin panel | As a admin | I want to log in securely to the admin panel |  | so I can access administrative functions. | High | 8 | Sachin | 1 day | 1 day | Complete
|  |  | As a admin | want to manage flight schedules (add, edit, delete) |  | can keep updated with current flight information. | High | 8 | Seshu | 3 days | 3 days | InProgress
|  |  | As a admin | I want to view and manage user accounts |  | so I can provide support and handle issues. | High | 8 | Venkatesh | 4 days | 4 days | Complete
|  |  | As a admin | I want to view and manage bookings |  | so I can monitor & modify reservations as needed. | Medium | 5 | Priyanka | 8 hrs | 1 day | InProgress
|  |  | As a admin | I want to receive alerts for critical system issues |  | so I can address them promptly. | Medium | 5 | Ragul | 1 day | 1 day | Complete
|  |  | As a admin | I want to manage discount codes and promotions |  | so I can offer deals to users | Medium | 5 | mayank | 1 day | 1 day | Complete
|  |  | As a admin | I want to monitor system logs and user activity |  | so I can ensure security and compliance. | High | 8 | Nivas | 1 day | 1 day | Complete
|  |  | As a admin | I want to manage payment settings and gateways |  | so I can ensure smooth transaction processing. | High | 8 | Priyanka | 2 day | 3 days | InProgress
User 6 |  | Cancel Booking | As a admin | I want to view my current booking |  | so that it allow user to view the current booking | High | 8 | Ragul | 2 day | 2 days | InProgress
|  |  | As a admin | I want to select a booking to cancel |  | so I can allow Booking they want to cancel | High | 8 | Sachin | 3 day | 3 days | Complete
|  |  | As a user | I want to confirm my cancellation |  | so I can verify foe cancellation | High | 8 | Priyanka | 3 day | 4 days | InProgress
|  |  | As a user | I want to Receive a refund |  | so I can get the refund amount. | Medium | 5 | Mayank | 2 day | 3 days | Complete
|  |  | As a user | I want to see a status should be updated to cancel |  | so I can see the user account booking status is cancelled | Medium | 5 | Nivas | 1 day | 1 days | InProgress
|  |  | As a admin | Cancelation process should be user friendly |  | so I can handle it easily | Medium | 5 | Seshu | 1 day | 1 days | InProgress

## Defect
Agile Project Planning - Online Flight Ticket Booking Defects
Defect id | Defect | Created on | Creator | Assigned to | Severity | Priority | Status
defect 01 | Unable to register | 2024-01-05 | Ragul | Priyanka | High | High | Open
defect 02 | Unable to login | 2024-02-16 | Priyanka | Sachin | Medium | High | Close
defect 03 | Unable to change password | 2024-02-19 | Rahul Nivas | Ragul | Medium | High | Open
defect 04 | Unable to booking flight tickets | 2024-03-07 | Sachin | Shalini | High | Medium | Open
defect 05 | Payment option not working | 2024-03-23 | Seshu | Rahul Nivas | Medium | High | Close
defect 06 | Notification msg are not receiving | 2024-04-10 | Mayank | Mayank | High | Medium | Open
defect 07 | Cancel flights tickets not working | 2024-05-03 | Shalini | Seshu | High | Medium | Close